Project Meeting 2

Global Analysis of BMI Trends in Adults and Newborns

PRESENTED BY

Group no-04

NATALIA MEJIA ALVAREZ (0872835)

SHALINI SIRDHALA (0875854)

JIE ZHANG (0879447)

PUSHP CHANDRASINH RATHAVA (0867974)

Subject

DAB422-26W-002 CAPSTONE PROJECT 2

PROFESSOR: Dr. Harpreet Virk

ST. CLAIR COLLEGE.

DATA ANALYTICS OF BUSINESS.

Project Name: AI-Driven Analysis of Global BMI Trends in Adults and Newborns (1990–2024)

Date and Time: January 30, 2026
Location: In Class – Zekelman Building
Time: 9:00 am – 10:30 am

Attendees:
Natalia Mejia Alvarez
Shalini Sirdhala
Jie Zhang
Pushp Chandrasinh Rathava

1. Weekly Summary

During Weeks 3 and 4, the team focused on preparing the WHO BMI datasets for Machine Learning and selecting initial modeling approaches.

In Week 3, we refined the cleaned data from Capstone 1 to ensure it was suitable for Machine Learning. We reviewed key variables, confirmed the dependent variable (NumericValue) and selected core features such as TimeDim (Year), ParentLocation (Region), SpatialDimensionValueCode (Country Code), and Sex. We also discussed whether to analyze adults and newborns together or separately and agreed to keep them separate due to different patterns and interpretation needs.

In Week 4, we selected and introduced the Machine Learning models that best align with the project objectives. We confirmed that our first ML direction will include:

- Regression models to quantify long-term BMI trends.

- Clustering (K-Means) to group countries with similar BMI patterns.

- Anomaly detection (Isolation Forest) to detect unusual BMI changes across years and regions.

We also aligned how results will be communicated through Tableau dashboards for stakeholder readability, with Python as the main tool for model development.

2. Individual Contributions

- Pushp: Focused on preprocessing steps and ensuring the dataset format supports model training. He also reviewed all the models working.

- Natalia: Organized feature selection and assisted with separating adult vs newborn datasets. Supported early trend analysis planning.

- Shalini: Worked on model selection discussion and defined how clustering could support regional comparison.

- Jie Zhang: Reviewed dataset variables and supported defining ML objectives aligned with public health outcomes.

- All Members: Participated in discussions, validated modeling direction, and agreed on next implementation steps.

3. Challenges and Solutions

- Feature consistency across datasets:
Adults and newborns share similar columns, but their value ranges behave differently, which we solved standardizing column names and decided to process each dataset separately before comparison.

- Text vs numeric BMI fields:
Some BMI fields include confidence interval text, which cannot be used directly in models, which we solved using Numeric Value as the primary modeling variable and kept intervals as context only.

- Risk of misleading clustering results:
Countries may cluster due to scale differences rather than true patterns, which we solved planning to apply scaling/normalization before clustering and compare clusters across multiple K values.

- Model selection alignment with project goals:
Many ML options exist, but not all support prescriptive insights, which we solved selecting models that directly support trend identification, segmentation, and anomaly detection for actionable public health interpretation.

4. Next Steps

- Start implementing initial regression trend models in Python.

- Apply scaling and test K-Means clustering on adult BMI first.

- Implement Isolation Forest to detect anomalies by region and year.

- Prepare initial Tableau visuals to summarize ML outputs in a stakeholder-friendly format.