Project Meeting Minutes 5

Project Name: A Global Study of BMI Patterns in Adults and Newborns.

| Date and Time | Location | Attendees |
| --- | --- | --- |
| November 10, 2025. | In Class, Zekelman Building. | NATALIA MEJIA ALVAREZ (0872835) |
| 9:00 am – 11: 00 am |  | SHALINI SIRDHALA (0875854) |
|  |  | JIE ZHANG (0879447) |
|  |  | PUSHP CHANDRASINH RATHAVA (0867974). |

#### 1. Weekly Summary

During this meeting, our team focused on the data analysis phase for the development of our Tableau dashboard. We worked with the WHO BMI datasets to explore global patterns and trends among adults and newborns. We cleaned and organized the dataset, calculated average BMI values by country, gender, and region, and then used Tableau to create a set of visualizations that highlight key insights.

BMI World Map: Displays the global distribution of average BMI by country, allowing us to identify regions with higher and lower BMI levels.

Top and Bottom 15 Countries: Bar charts showing the countries with the highest and lowest average BMI in 2024.

Gender Comparison: A comparison of average BMI values between males, females, and both sexes combined.

Regional Trend: A line chart showing BMI evolution across major world regions from 1990 to 2024.

Global BMI Trend: A global trendline comparing average BMI with the healthy BMI range, revealing a steady increase over the years.

BMI Distribution by Year: Shows the distribution of BMI values over time, emphasizing the median trend across years.

All members actively participated in discussions and contributed to finalizing the content.

#### 2. Individual Contributions

- Natalia: Worked on visualizations by gender and location.

- Pushp: Worked on visualizations on python, data cleaning and setting up the final dashboard.

- Shalini: Worked on visualization about timeline and year.

- Jie Zhang: Worked on visualization by DMI – trends and averages.

- All Members: Participated in discussions, provided feedback, and jointly approved the finalized outputs.

#### 3. Challenges and Solutions

- Some columns had uncleared or mixed labels. We standardized variable names and cleaned the dataset to ensure consistency.

- Large Dataset: The file contained many years and countries, slowing Tableau. We aggregated data by region and year to improve performance.

- Missing Values: Some countries had incomplete BMI data. We used nearby year averages or excluded missing entries to keep results reliable.

- Visualization Clarity: Early charts were hard to interpret. We changed chart types, added color gradients, and improved labeling for better readability.

- Mixed Age Groups: Combining adults and newborns caused confusion due to different BMI standards. We separated both datasets to analyze them independently.

#### 4. Next Steps

- Finalize EDA

- Working on ML modeling directions.

- Feedback on visualizations.